## Sample Sprint
Sprint planner & Jira Integrator v4.0 by Twin Pigs Agile Studio |  | This template is a part of the Twin Pigs Agile Process v1
Configuration |  | System state |  |  |  |  | Sprint total |  |  | Left in sprint |  |  | Postponed (clipboard area) |  |  | Sprint configuration
Start date cell | AU5 | Locked | FALSE |  |  |  | Group | Dev | Test | Group | Dev | Test | Group | Dev | Test
Sprint length cell | AU6 | Day | 2025-03-21 |  |  |  | DC | 8 | 8 | Focus | 8 | 8 | Focus | 8 | 8 | Start date | 2025-03-18
Inverted workdays range | AU7:BZ7 | Status: | Data unlocked |  |  |  | WRW | 1.5 | 1.5 | Multiplier | 1.5 | 1.5 | Multiplier | 1.5 | 1.5 | Sprint length (days) | 10
Sprint total estimate range | K7:T7 | [5 empty] | TPSP | 0 | 0 | Total SP | 0 | 0 | Total SP | 0 | 0 | Inverted workdays
Sprint remaining estimate range | W7:AF7 | [5 empty] | Days | 0 | 0 | Days | 0 | 0 | Days | 0 | 0
Sprint burndown data range | BE19:BZ118
Sprint burndown header range | BE18:BZ18
Days left range | W8:AF8 | Actions: | Please select an action cell and click RUN. Do not forget to use a VPN and proxy for Jira interactions. |  |  | #VALUE!
Initial days range | K8:T8 |  | RECALC | UPDATE
Sprint scope range | K19:T218 |  | LOCK | UNLOCK
Issue remaining estimates range | W19:AF218 |  | FROM JIRA | TO JIRA
Postponed range | AI19:AR218 |  | CONFIG | APPLY
Issue keys range | H19:H218
Summaries range | G19:G218 | Issues |  |  |  |  | Estimates area | [8 empty] | Burndown
Resolved range | D19:D218 | Resolved, R/O | Assignee, R/O | Prefix, 3 sym | Summary | Key, R/O |  | Dev | Test |  | Dev | Test |  | Dev | Test |  |  | # | Date | D, plan | T, plan | D | T
Assignees range | E19:E218 | [16 empty] | 1 | 2025-03-18 | 0 | 0
Prefix range | F19:F218 | [16 empty] | 2 | 2025-03-19 | 0 | 0
Jira proxy | http://localhost:8080 | [16 empty] | 3 | 2025-03-20 | 0 | 0
Lock cell | E4 | [16 empty] | 4 | 2025-03-21 | 0 | 0
JQL | sprint="Sample Sprint 1" ORDER BY key | [16 empty] | 5 | 2025-03-24 | 0 | 0
Resource groups | 2 | [16 empty] | 6 | 2025-03-25 | 0 | 0
Group codes | D,T | [16 empty] | 7 | 2025-03-26 | 0 | 0
Group names | Dev,Test | [16 empty] | 8 | 2025-03-27 | 0 | 0
Group names ranges | K4:T4,W4:AF4,AI4:AR4,K18:T18,W18:AF18,AI18:AR18 | [16 empty] | 9 | 2025-03-28 | 0 | 0
Today cell | E5 | [16 empty] | 10 | 2025-03-31 | 0 | 0
Message cell | E6 | [16 empty] | 11 | 2025-04-01 | 0 | 0
RUN
Note on E4: When it's TRUE, you can UPDATE. When it's FALSE, you can RECALC. Triggered by LOCK/UNLOCK.
Note on J5: Daily Capacity. The number of working hours the resource group has daily.
Note on AT5: The sprint start date
Note on J6: Ideal working hours/TPSPs can never be mapped to the real ones 1:1. The coefficient reflects how many real working hours you expect to spend to do a work that has been planned as an 1-hour (1SP) work. WRW stands for "Welcome to the Real World."
Note on AT6: The desired sprint length (in days)
Note on J7: Twin Pigs Story Points (Ideal working hours)
Note on AT7: Normally Saturdays and Sundays are non-working days, and they are not incluided into the sprint schedule, while all the others are used for planning. However, sometimes you have working Saturdays and Sundays as well as non-working days Monday to Friday. List all such days here.
Note on E12: Calculates the sprint and prepares the burndown. Does not clear the burndown data, so may be used to update the graph ater the sprint has been started. Clear the burndown data manually if needed.
Note on F12: Reim, Elijah: Update burndown for today
Note on E13: Locks the sprint scope. You will not be able to run "RECALC" until you run "UNLOCK".
Note on F13: Reim, Elijah: Unlock sprint scope
Note on E14: CAUTION! Loads the estimates from Jira! All the estimates that were not exported earlier using "TO JIRA" will be lost! Reloads the issue list from JIRA. Needs proxy. May need a VPN connection.
Note on F14: Exports edited values to Jira
Note on E15: Show config
Note on F15: Apply changes and hide config
Note on B27: First you should enumerate 3 ranges used for formulas, then the others